## Gantt Chart
PROJECT TITLE Automated Toolbox Inventory Control System COMPANY NAME Null Terminators PROJECT MANAGER Reem Osman |  |  |  |  | GANTT CHART
WBS NUMBER | TASK TITLE | Task Owner | START DATE [Week starting in] | DUE DATE [Week starting in] | DURATION [Hours] | September | October |  |  |  |  | November |  |  |  |  | December |  |  |  |  | January |  |  |  |  | Feburary |  |  |  |  | March |  |  |  |  | April |  |  |  |  | May
[6 empty] | WEEK OF 9/25 | WEEK OF 10/2 | WEEK OF 10/9 | WEEK OF 10/16 | WEEK OF 10/23 | WEEK OF 10/30 |  | WEEK OF 11/6 | WEEK OF 11/13 | WEEK OF 11/20 | WEEK OF 11/27 |  | WEEK OF 12/4 | WEEK OF 12/11 | WEEK OF 12/18 | WEEK OF 12/25 | WEEK OF 1/1 | WEEk OF 1/8 | WEEK OF 1/15 | WEEK OF 1/22 | WEEK OF 1/29 |  | WEEK OF 2/5 | WEEK OF 2/12 | WEEk OF 2/19 | WEEK OF 2/26 |  | WEEK OF 3/4 | WEEK OF 3/11 | WEEK OF 3/18 | WEEK OF 3/25 | WEEK OF 4/1 | WEEK OF 4/8 | WEEK OF 4/15 | WEEK OF 4/22 | WEEK OF 4/29
1 | Project Plan
1.1 | Understand problem domain | Reem Osman | 2023-09-25 | 2023-09-25 | 2
1.1.1 | Determine scope | Reem Osman | 2023-10-02 | 2023-10-30 | 5
1.2 | Identify tasks | Reem Osman | 2023-09-25 | 2023-11-06 | 3
1.3 | Estimate time to perform tasks | Reem Osman | 2023-11-06 | 2023-11-13 | 2
1.4 | Schedule tasks | Reem Osman | 2023-11-13 | 2023-11-13 | 5
1.5 | Write Project Plan | Reem Osman | 2023-10-09 | 2023-11-13 | 18
1.5.1 | Write Introduction | Reem Osman | 2023-11-06 | 2023-11-13 | 1
1.5.2 | Write Scope | Reem Osman | 2023-10-09 | 2023-10-30 | 5
1.5.3 | Write Approach | Reem Osman | 2023-11-06 | 2023-11-13 | 1
1.5.4 | Write Estimate | Reem Osman | 2023-10-30 | 2023-11-13 | 10
1.5.5 | Add figures, references, and miscellanea | Reem Osman | 2023-11-13 | 2023-11-13 | 1
1.6 | Review project plan | Reem Osman | 2023-11-13 | 2023-11-13 | 2
1.7 | Present Project Plan to HiLine | Reem Osman | 2023-11-13 | 2023-11-13 | 2
2 | Research and Preparation
2.1 | Research cameras | Caitlyn Powers | 2023-10-23 | 2023-11-27 | 12
2.1.1 | Research camera requirements | Caitlyn Powers | 2023-10-23 | 2023-10-30 | 4
2.1.2 | Calculate/ create a guess for minimum camera requirements | Caitlyn Powers | 2023-10-23 | 2023-11-06 | 4
2.1.3 | Research cameras that meet those requirements | Caitlyn Powers | 2023-10-23 | 2023-11-20 | 4
2.2 | Research how to request sample cameras | Caitlyn Powers | 2023-11-13 | 2023-11-27 | 4
2.3 | Select cameras | Caitlyn Powers | 2023-11-13 | 2023-11-27 | 5
2.3.1 | Request cameras | Reem Osman | 2023-12-11 | 2023-12-04 | 2
2.4 | Get cameras and Assemble | Caleb Thomas | 2024-01-22 | 2024-01-29 | 1
2.5 | Research Opencv python | Caitlyn Powers | 2023-10-02 | 2023-10-16 | 3
2.6 | General testing for opencv python | Caitlyn Powers | 2023-10-16 | 2023-12-25 | 14
2.6.1.1 | Experment with segmentation | Caitlyn Powers | 2023-10-16 | 2023-11-13 | 4
2.6.1.2 | Experiment with template matching | Caitlyn Powers | 2023-12-11 | 2023-12-25 | 6
2.6.1.3 | Experiment with ONNX | Caitlyn Powers | 2023-10-16 | 2023-10-30 | 4
2.7 | Research pytorch | Steven Pixler | 2023-10-02 | 2023-10-02 | 1
2.8 | Gather data in the form of pictures of tools and sorting them | Steven Pixler | 2023-10-02 | 2023-10-09 | 4
2.9 | Symbol Experimentation | Caitlyn Powers | 2024-01-22 | 2024-02-26 | 13
2.9.1 | Test varouse non-machine learing symbol recognition methods | Caitlyn Powers | 2024-01-22 | 2024-02-26 | 6
2.9.2 | Test machine learning symbol recognition methods | Steven Pixler | 2024-02-05 | 2024-02-26 | 5
2.9.3 | Create videos for symbol recognition experimentation | Caleb Thomas | 2024-01-22 | 2024-02-19 | 2
3 | Requirement Specfication
3.1 | Develop Prox Card Interface API | Caleb Thomas | 2023-11-27 | 2023-12-04 | 6
3.1.1 | Designate format of API Event: Box unlock | Caleb Thomas | 2023-11-27 | 2023-12-04 | 3
3.1.2 | Designate format of API Event: Box lock | Navin Saban... | 2023-12-04 | 2023-12-04 | 3
3.2 | Determine database performance targets | Navin Saban... | 2023-12-04 | 2023-12-04 | 2
3.3 | Write Requirement Specification Document | Reem Osman | 2023-11-27 | 2023-12-04 | 15
3.3.1 | Illustrate UML Diagrams (Use case/Class diagram/Sequence diagram) | Reem Osman | 2023-11-27 | 2023-12-04 | 5
3.4 | Present Requirement Specification Document | Reem Osman | 2023-12-04 | 2023-12-04 | 1
4 | Design
4.1 | Design tests for cameras | Caitlyn Powers | 2024-01-15 | 2024-01-22 | 3
4.2 | Set up local python environment | Caitlyn Powers | 2024-01-08 | 2024-01-15 | 1
4.3 | Design configuration files | Caitlyn Powers | 2024-02-19 | 2024-02-26 | 4
4.4 | Design drawer recognition | Caitlyn Powers | 2024-02-05 | 2024-03-04 | 4
4.5 | Design template match | Caitlyn Powers | 2024-01-29 | 2024-02-26 | 4
4.6 | Design helper functions | Caitlyn Powers | 2024-02-05 | 2024-03-04 | 4
4.7 | Design tool recognition | Caitlyn Powers | 2024-02-26 | 2024-03-04 | 4
4.8 | Design Database Schema | Navin Saban... | 2024-01-08 | 2024-01-29 | 20
4.8.1 | Design Tool Table Schema | Navin Saban... | 2024-01-08 | 2024-01-15 | 10
4.8.2 | Design Drawers Table Schema | Caleb Thomas | 2024-01-22 | 2024-01-22 | 6
4.8.3 | Design Events Table Schema | Navin Saban... | 2024-01-29 | 2024-01-29 | 4
4.9 | Design Database API | Caleb Thomas | 2024-02-05 | 2024-02-19 | 15
4.9.1 | Design Tools Database Interface | Navin Saban... | 2024-02-05 | 2024-02-05 | 5
4.9.2 | Design Drawers Database Interface | Caleb Thomas | 2024-02-12 | 2024-02-12 | 5
4.9.2 | Design Events Table Interface | Caleb/Navin | 2024-02-19 | 2024-02-19 | 5
5 | Implementation
5.1 | Implement configuration files | Caitlyn Powers | 2024-03-04 | 2024-03-25 | 4
5.2 | Implement tool recognition | Caitlyn Powers | 2024-03-11 | 2024-04-08 | 6
5.3 | Implement helper function | Caitlyn Powers | 2024-02-26 | 2024-03-25 | 6
5.4 | Implement drawer recognition | Caitlyn Powers | 2024-02-26 | 2024-03-11 | 6
5.5 | Implement template matching | Caitlyn Powers | 2024-01-29 | 2024-02-19 | 6
5.6 | Integrate with tool recognition model | Caitlyn Powers | 2024-03-11 | 2024-04-01 | 4
5.7 | Install SQL server | Caleb Thomas | 2024-03-18 | 2024-04-01 | 11
5.7.1 | Install SQL server software | Caleb Thomas | 2024-03-18 | 2024-03-25 | 3
5.7.2 | Create Tools database | Caleb Thomas | 2024-03-18 | 2024-03-25 | 3
5.7.3 | Integrate with prox card API | Caleb Thomas | 2024-03-18 | 2024-03-25 | 5
5.8 | Configure SQL Server | Caleb Thomas | 2024-03-18 | 2024-03-25 | 6
5.8.1 | Configure Tools Table | Caleb Thomas | 2024-03-18 | 2024-03-25 | 2
5.8.2 | Configure Drawers Table | Caleb Thomas | 2024-03-18 | 2024-03-25 | 2
5.8.3 | Configure Events Table | Caleb Thomas | 2024-03-18 | 2024-03-25 | 2
5.9 | Write Database API | Navin Saban... | 2024-03-18 | 2024-03-25 | 24
5.9.1 | Write Tools Database Interface | Navin Saban... | 2024-03-18 | 2024-03-18 | 8
5.9.2 | Write Drawers Database Interface | Navin Saban... | 2024-03-18 | 2024-03-18 | 8
5.9.3 | Write Events Database Interface | Navin Saban... | 2024-03-25 | 2024-03-25 | 8
5.10 | Integrate tool monitoring code with database | Caitlyn Powers | 2024-04-01 | 2024-04-08 | 3
5.11 | Write classifier code using PyTorch for tool image recognition | Steven Pixler | 2023-10-02 | 2024-03-25 | 5
6 | Testing
6.1 | Test cameras | Caleb Thomas | 2024-01-29 | 2024-02-19 | 8
6.2 | Set up testing area | Reem Osman | 2024-02-05 | 2024-04-15 | 8
6.3 | Take initial pictures for testing | Steven Pixler | 2024-02-26 | 2024-03-04 | 2
6.4 | Take initial videos for testing | Steven Pixler | 2024-02-26 | 2024-03-04 | 2
6.5 | Test drawer recognition with camera footage | Caitlyn Powers | 2024-03-04 | 2024-03-25 | 4
6.6 | Test tool match with camera footage | Caitlyn Powers | 2024-03-25 | 2024-04-08 | 4
6.7 | Test tool recognition with camera footage | Caitlyn Powers | 2024-03-25 | 2024-04-08 | 4
6.8 | Test helper functions with camera footage | Caitlyn Powers | 2024-03-25 | 2024-04-08 | 4
6.9 | Test integration with tool recognition model with camera footage | Caitlyn Powers | 2024-03-25 | 2024-04-08 | 4
6.1 | Test integration with database | Caitlyn Powers | 2024-03-25 | 2024-04-15 | 5
6.11 | Final testing | Reem Osman | 2024-04-08 | 2024-04-15 | 8
6.11.1 | Final testing before delivery | Reem Osman | 2024-04-08 | 2024-04-15 | 6
6.11.2 | Program Demo | Reem Osman | 2024-04-15 | 2024-04-15 | 2
7 | User Guide
7.1 | Configuration Guide | Reem Osman | 2024-04-15 | 2024-04-22 | 4
7.2 | Write User Guide | Reem Osman | 2024-04-22 | 2024-04-29 | 4
8 | Project Summary
8.1 | Write Project Summary Semester 1 | Reem Osman | 2023-12-11 | 2023-12-11 | 2
8.2 | Write Project Summary Semester 2 | Reem Osman | 2024-04-29 | 2024-04-29 | 2